## User Stories
User Story ID | User Story | Acceptance Criteria | Acceptance Criterion ID | Imple-men-ted?
1A(1) | As an unauthenticated user, I want to visit the CJT website, so I can identify a tour I might be interested in taking. | Given: that the user is on the home page, when they select current tours, then they should see a list with all the details for each tour. | AC-03 | Y
1A(2) | As an unauthenticated user, I want to visit the CJT website, to view a brief description of the guides. | Given that the user is on the home page, when they click on guides, then they should be navigated to the guides section. | AC-05 | Y
1A(3) | As an unauthenticated user, I want to visit the CJT website, to view all the places the company offers to visit | Given that the user is on the home page, when they click on stops, then they should be navigated to the key stops section. | AC-02 | Y
2A | As a user, I want to login, so I can secure my information. | Given the login credentials are valid, When the user clicks login, Then the user should be redirected to the tours page. | AC-01 | Y
2B(1) | As a user, I want to login, so I can browse and book available routes/guides. | Given the login credentials are valid, When the user login, Then the user should be able to view available guides and routes. | AC-04 | N
2B(2) | As a user, I want to manage my booked tours, so I can edit or cancel them. | Given the user booked a tour, When the user views the details of the booked tour, Then the user should be able to edit or cancel it. | AC-08 | N
2B(3) | As a user, I want to view my previous tours, so I can leave a review/rating. | Given the user has booked tours in the past, When the user views previous routes, Then the user should be able to leave a review and rate their tour guides. | AC-09 | N
3A(1) | As a visitor, I want to register, so that i can use the site's features | Given the registration details are valid, When the visitor submits the request, Then an account will be created with my details. | AC-11 | Y
4A1 | As a user, I want to logout, so that no one else has my information. | Given that the user is signed in, when clicking "Logout" , then they should be redirected to the home page and required to login to access their information. | AC-06 | Y
4A2 | As an authenticated guide, I want to prevent unauthorized access to my tours, so I can use the company's services knowing that my tours setup is not compromised. | Given that the guide is signed in, when clicking "Logout" , then they should be redirected to the home page and required to login to access their information. | AC-07 | Y
5A | As a guide, I want to login, so that i can get to my information | Given the login credentials are valid, When the guide clicks login, Then the user should be redirected to the my tours page. | AC-10 | Y
5A(1) | As a guide, I want to login, so that i can add a tour | Given the login credentials are valid, When the guide logs in, Then the guide should be able to add a new tour. | AC-11 | Y
5A(2) | As a guide, I want to login, so that i can update a tour | Given the login credentials are valid, When the guide logs in, Then the guide should be able to update a tour. | AC-12 | Y
5A(3) | As a guide, I want to login, so that i can delete a tour | Given the login credentials are valid, When the guide logs in, Then the guide should be able to delete a tour. | AC-13 | Y

## Requirements
User Story ID | Module Name | Requirement Description | Requirement ID
1A1 | Home | Current Tours clickable element displays all tours | BR-101
1A2 | Home | Our guides clickable element scrolls to the guides section | BR-102
1A3 | Home | Popular stops link scrolls in view the stops set by website manager. | BR-103
2A1 | Home | At least one guide is present in the system | BR-104
2A1 | Home | A picture and a brief description will be available for each guide | BR-105
4A1 | User | The status of the visiting user should be available by a clickable link in the top right corner of the screen on the landing page | BR-106
4A1 | Logout | Logging out navigates the user to the home page and delete data from browser. | BR-107
2A1 | Tours | A minimum of three point-of-interest is required to identify a route | BR-108
3A1 | Tours | A tour-route is identified by the selected POI if they are contained by the route regardless of their order | BR-109
3A1 | Tours | Email address is associated with a user account | BR-110
3A1 | Tours | Email & password combination is correct | BR-111
3A1 | Tours | Day of the week must be selected | BR-112
3A1 | Tours | Routes must contain at least three points of interest defined by the company | BR-113
3A1 | Tours | Rates must be positive numbers with maximum two decimal places and less than 100 | BR-114
3A1 | Tours | A tour title must be entered | BR-115
3A1 | Tours | Day of the week must be selected | BR-116
3A1 | Tours | Routes must contain at least three points of interest defined by the company | BR-117
3A1 | Tours | Rates must be positive numbers with maximum two decimal places and less than 100 | BR-118
3A1 | Tours | The tour status must be selected | BR-119
2A(4) | Tours | Only the owning guide role account can delete the tour. | BR-120
3A | Registration | Email must not be blank | BR-121
3A | Registration | Email must not already be used by another user | BR-122
3A | Registration | Password must not be blank | BR-123
3A | Registration | Password must have a minimum of 8 characters and a maximum of 20 characters | BR-124
3A | Registration | Password must have at least 1 lowercase and 1 uppercase alphabetical character | BR-125
3A | Registration | Password must have at least 1 numeric character | BR-126
3A | Registration | Password must have at least 1 special character !@#$%^&*_ | BR-127
3A | Registration | First name must not be blank | BR-128
3A | Registration | First name must contain only alphabetical characters | BR-129
3A | Registration | First name must be at least 2 characters long and not longer than 30 | BR-130
3A | Registration | Last name must not be blank | BR-131
3A | Registration | Last name must contain only alphabetical characters | BR-132
3A | Registration | Last name must be at least 2 characters long and not longer than 30 | BR-133
3A | Registration | Phone number must not be blank | BR-134
3A | Registration | Phone number must have format XXX-XXX-XXXX | BR-135
3A | Registration | Email address must have format <username>@<domain> | BR-136

## Test scenarios
User Story ID | Test Scenario ID | Scenario description | Requirement ID
1A1 | T-101 | Signing up successfully with a user account and loading the landing page | BR-101, BR-106
4A1 | T-102 | User performs logout | BR-107
2A1 | T-103 | Successful login | BR-111
2A1 | T-104 | Invalid email | BR-110
2A1 | T-105 | Invalid password | BR-110
2A1 | T-106 | Blank email | BR-110, BR-111
2A1 | T-107 | Blank password | BR-110, BR-111
2A1 | T-108 | Invalid email and password | BR-110, BR-111
3A1 | T-109 | Signing up successfully | BR-121:BR-136
3A1 | T-110 | Blank email | BR-121
3A1 | T-111 | Blank password | BR-123
3A1 | T-112 | Blank first name | BR-128
3A1 | T-113 | Blank last name | BR-131
3A1 | T-114 | Blank phone | BR-134
3A1 | T-115 | Email already taken | BR-122,
3A1 | T-116 | Email invalid format | BR-136
3A1 | T-117 | Name invalid format | BR-129, BR-130, BR-132, BR-133
3A1 | T-118 | Phone invalid format | BR-135
3A1 | T-119 | Password invalid format | BR-123:BR-127
2A2 | T-120 | Signing up successfully with a guide account and loading the landing page | BR-106
2A3 | T-121 | Add a tour using valid data | BR-112:BR-115
2A3 | T-122 | Blank price | BR-114
2A3 | T-123 | Blank title | BR-115
2A3 | T-124 | Update successfully using valid data | BR-112:BR-115
2A3 | T-125 | Update a tour without selecting a valid number of points of interest | BR-113
2A3 | T-126 | Blank price | BR-114
2A3 | T-127 | Unselected tour status | BR-114
2A3 | T-128 | Delete tour | BR-120
1A2 | T-129 | Click Our guides on any page | BR-102

## test cases
Test Case ID | Test Case Description | Test Steps | Test Data | Expected Results | Actual result | Pass/Fail | Defect ID | Comments
TC-101 | While signing up valid data is entered in the form. | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field 6. click register | email = t@t.ca password = Password123! First name = li last name = liu Phone = 123-123-1234 | User is logged in and navigated to the user landing page showing a list of all the tours | User is logged in and navigated to the user landing page showing a list of all the tours | pass
TC-102 | While signed in user performs logout then click back button. | 1. type email in email field 2. type password in the password field 3.click login 4. logout 5.click back button | email = vv@a.ca password = Password123! | User is signed out and navigated to the home page, when clicking back button user should not navigat to the guide landing page but to the login page. | Guide is signed out and navigated to the home page, when clicking the back button the guide tours list is displayed. | FAIL | D-01 | If session information is missing the endpoint should return a 404 user not found when loading table data.
TC-103 | While selecting login a user provides valid credentials and successfully signs in | 1. type email in email field 2. type password in the password field 3.click login | email = t@t.ca password = Password123! | User is signed in and a list with all the available tours is shown | User is signed in and a list with all the available tours is shown | pass
TC-104 | Invalid email | 1. type email in email field 2. type password in the password field 3.click login | email = x@t.ca password = Password123! | "Invalid email and/password combination " is shown. | "Invalid email and/password combination " is shown. | pass
TC-105 | Invalid password | 1. type email in email field 2. type password in the password field 3.click login | email = x@t.ca password = Password123! | "Invalid email and/password combination " is shown. | "Invalid email and/password combination " is shown. | pass
TC-106 | Blank email | 1. click login | email = password = Password123! | "Email cannot be empty " is shown. | "Email cannot be empty " is shown. | pass
TC-107 | Blank password | 1. type email in email field 2.click login | email = x@t.ca password = | "Password cannot be empty " is shown. | "Password cannot be empty " is shown. | pass
TC-108 | Invalid email and password | 1. type email in email field 2. type password in the password field 3.click login | email = x@t.ca password = Password123!1 | "Invalid email and/password combination " is shown. | "Invalid email and/password combination " is shown. | pass
TC-109 | Signing up successfully | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = tt@t.ca password = Password123! First name = li last name = liu Phone = 123-123-1234 | User is logged in and navigated to the user landing page showing a list of all the tours | User is logged in and navigated to the user landing page showing a list of all the tours | pass
TC-110 | Blank email | 1. type email in email field 2.type first name in first name field 3. type lastname into last name field 4. type phone in phone field 5. click register | email = password = Password123! First name = li last name = liu Phone = 123-123-1234 | "Email cannot be empty " is shown. | "Email cannot be empty " is shown. | pass
TC-111 | Blank password | 1. type email in email field 2.type first name in first name field 3. type lastname into last name field 4. type phone in phone field 5. click register | email = tt@t.ca password = First name = li last name = liu Phone = 123-123-1234 | "password cannot be empty " is shown. | "password cannot be empty " is shown. | pass
TC-112 | Blank first name | 1. type email in email field 2. type password in the password field 3. type lastname into last name field 4. type phone in phone field 5. click register | email = tt@t.ca password = Password123! First name = last name = liu Phone = 123-123-1234 | "First name cannot be empty " is shown. | "First name cannot be empty " is shown. | pass
TC-113 | Blank last name | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type phone in phone field 5. click register | email = tt@t.ca password = Password123! First name = li last name = Phone = 123-123-1234 | "Last name cannot be empty " is shown. | "Last name cannot be empty " is shown. | pass
TC-114 | Blank phone | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. click register | email = tt@t.ca password = Password123! First name = li last name = liu Phone = | "Phone cannot be empty " is shown. | "Phone cannot be empty " is shown. | pass
TC-115 | Email already taken | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = tt@t.ca password = Password123! First name = li last name = liu Phone = 123-123-1234 | "An email address can only be used once to register" is shown. | "An email address can only be used once to register" is shown. | pass
TC-116 | Email invalid format | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = ttt.ca password = Password123! First name = li last name = liu Phone = 123-123-1234 | "Accepted email format is <username>@<domain>" is shown. | "Accepted email format is <username>@<domain>" is shown. | pass
TC-117 | Name invalid format | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = tt@t.ca password = Password123! First name = l last name = liu Phone = 123-123-1234 | "The name must be at least 2 latin alphabet characters long and less than 31" is shown. | "The name must be at least 2 latin alphabet characters long and less than 31" is shown. | pass
TC-118 | Phone invalid format | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = tt@t.ca password = Password123! First name = li last name = liu Phone = 0123-123-1234 | "Accepted email format is xxx-xxx-xxxx" is shown. | "Accepted email format is xxx-xxx-xxxx" is shown. | pass
TC-119 | Password invalid format | 1. type email in email field 2. type password in the password field 3.type first name in first name field 4. type lastname into last name field 5. type phone in phone field | email = tt@t.ca password = Password! First name = li last name = liu Phone = 0123-123-1234 | "The password must contain at least 1 lowercase character, at least one upper case character, one number and one special carracter from the numeric keys, and a total length between 8 and 20 inclusive. " is displayed. | "The password must contain at least 1 lowercase character, at least one upper case character, one number and one special carracter from the numeric keys, and a total length between 8 and 20 inclusive. " is displayed. | pass
TC-120 | Signing up successfully with a guide account and loading the landing page | 1. type email in email field 2. type password in the password field 3.click login | email = vv@t.ca password = Password123! | A list with only the tours owned by the guide is shown. | A list with only the tours owned by the guide is shown. | pass
TC-121 | Add a tour using valid data | 1. sign in a guide user 2. click Add Tour 3. select the day of the week 4. select three points of interest 5. type the price 6. type the title 7. click add tour | day = Wednesday select 3 access points price=66 title=test-title | A confirmation alert is shown and the guide is navigated back to their landing page while the newly added tour is part of the guide's tours list. | A confirmation alert is shown and the guide is navigated back to their landing page while the newly added tour is part of the guide's tours list. | pass
TC-122 | Blank price | 1. sign in a guide user 2. click Add Tour 3. select the day of the week 4. select three points of interest 5. type the price 6. type the title 7. click add tour | day = Wednesday select 3 access points price= title=test-title | "Price cannot be empty " is shown. | "Price cannot be empty " is shown. | pass
TC-123 | Blank title | 1. sign in a guide user 2. click Add Tour 3. select the day of the week 4. select three points of interest 5. type the price 6. type the title 7. click add tour | day = Wednesday select 3 access points price=66 title= | "Title cannot be empty " is shown. | "Title cannot be empty " is shown. | pass
TC-124 | Update successfully using valid data | 1. sign in a guide user 2. click Update Tour in the Tours list 3. select the day of the week 4. select three points of interest 5. type the price 6. Select a tour status 7. click update tour | day = Sunday select 3 access points price=66 status=Active | A confirmation alert is shown and the guide is navigated back to their landing page while the recently updated tour is part of the guide's tours list. | A confirmation alert is shown and the guide is navigated back to their landing page while the recently updated tour is part of the guide's tours list. | pass
TC-125 | Update a tour without selecting a valid number of points of interest | 1. sign in a guide user 2. click Update Tour in the Tours list 3. select the day of the week 4. select three points of interest 5. type the price 6. Select a tour status 7. click update tour | day = Sunday select 6 access points price=66 status=Active | "Sellect between 3 and 5 points of intrest to validate this request" is shown. | "Sellect between 3 and 5 points of intrest to validate this request" is shown. | pass
TC-126 | Blank price | 1. sign in a guide user 2. click Update Tour in the Tours list 3. select the day of the week 4. select three points of interest 5. type the price 6. Select a tour status 7. click update tour | day = Sunday select 3 access points price= status=Active | "Price cannot be empty " is shown. | "Price cannot be empty " is shown. | pass
TC-127 | Unselected tour status | 1. sign in a guide user 2. click Update Tour in the Tours list 3. select the day of the week 4. select three points of interest 5. type the price 6. Select a tour status 7. click update tour | day = Sunday select 3 access points price=66 status= | "Either active or inactive tour status must be selected " is shown. | "Either active or inactive tour status must be selected " is shown. | pass
TC-128 | Delete tour | 1. sign in a guide user 2. click delete in the Tours list |  | The tour is removed from the list on page reload | The tour is removed from the list on page reload | pass
TC-129 | Click Our guides on any page | 1. Click "Our guides" |  | User is navigated to the home page and guides section is scrolled into view | User is navigated to the home page and guides section is scrolled into view | pass

## requirements traceability matix
Test Case ID | Test Scenario ID | Requirement ID
TC-101 | T-101 | BR-101, BR-106
TC-102 | T-102 | BR-107
TC-103 | T-103 | BR-111
TC-104 | T-104 | BR-110
TC-105 | T-105 | BR-110
TC-106 | T-106 | BR-110, BR-111
TC-107 | T-107 | BR-110, BR-111
TC-108 | T-108 | BR-110, BR-111
TC-109 | T-109 | BR-121:BR-136
TC-110 | T-110 | BR-121
TC-111 | T-111 | BR-123
TC-112 | T-112 | BR-128
TC-113 | T-113 | BR-131
TC-114 | T-114 | BR-134
TC-115 | T-115 | BR-122,
TC-116 | T-116 | BR-136
TC-117 | T-117 | BR-129, BR-130, BR-132, BR-133
TC-118 | T-118 | BR-135
TC-119 | T-119 | BR-123:BR-127
TC-120 | T-120 | BR-106
TC-121 | T-121 | BR-112:BR-115
TC-122 | T-122 | BR-114
TC-123 | T-123 | BR-115
TC-124 | T-124 | BR-112:BR-115
TC-125 | T-125 | BR-113
TC-126 | T-126 | BR-114
TC-127 | T-127 | BR-114
TC-128 | T-128 | BR-120
TC-129 | T-129 | BR-102

## defect log
Defect ID | Test Case ID | Defect Description | Steps | Detected By | Date Raised | Assigned to | Status | Fixed By | Date Closed | Severity | Priority
D-1 | TC-102 | After Guide is signed out and navigated to the home page, when clicking the back button the guide tours list is displayed. | 1. type email in email field 2. type password in the password field 3.click login 4. logout 5.click the browser back button | Valentin | 2022-08-14 | Chris | Open |  |  | High | High

## Report
Test Report
Test Cycle | Manual tests | 1 | 1 | 0
| Automation framework | 108 | 108 | 108
EXECUTED | Unit tests | 18 | 18 | 18
| FAILED |  | 1
| (Total) TESTS EXECUTED (PASSED + FAILED) |  |  | 127
PENDING |  |  |  | 0
IN PROGRESS |  |  |  | 0
BLOCKED |  |  |  | 0
(Sub-Total) TEST PLANNED
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED) |  |  |  | 127
Functions | Description | % TCs Executed | % TCs Passed | TCs pending | Priority | Remarks
Login | Check User Login | 100% | 95% | 1 | High
Registration | Check Registration | 100% | 100% | 0 | High
All tours | Check All tours / User landing page | 100% | 100% | 0 | High
Guide landing page | Check Guide landing page | 100% | 100% | 0 | High
Add Tour | Check Add Tour | 100% | 100% | 0 | High
Update Tour | Check Update Tour | 100% | 100% | 0 | High
Delete Tour | Check tours list | 100% | 100% | 0 | High